# Service Plan Launch Kit

Cowboy's Air Conditioning & Heating

Tiered Membership Program · Basic / Comfort / Comfort+

Prepared by Michael Scott Lopez · June 8, 2026

# Executive Summary

Cowboy's currently has zero recurring revenue from service plans. With 39,951 customers in the database and 5,378 jobs per year already coming from Previous Customers, the foundation for a membership program is already in place — it's a matter of turning on the program and migrating the existing repeat-customer relationships into recurring billing.

This kit covers three tiered plans (Basic / Comfort / Comfort+), the financial model behind them, the operational rollout, the CSR/tech pitch, and the customer-facing one-pager. At a conservative 10% adoption rate (4,000 members), projected Year-1 revenue is $1.71M with $1.34M contribution margin (78%). At 20% adoption it doubles.

## Why now

- Previous Customers already generate 35% of jobs ($4.79M/yr) — they're buying repeat service, just not on a structured plan.

- Average ticket has climbed to $1,300+ since Feb 2026, which means customers are comfortable spending more — they'll value the discount tied to membership.

- Cancellation rate doubled (3.4% → 7.2%) in 8 months. Members cancel 60-80% less often because they're paying monthly and want the value.

- Heating season (Nov-Jan) revenue is 36% below summer. Memberships create demand that runs through the trough.

# 1. The Three Plan Tiers

Three is the right number — fewer hides the upsell, more confuses the customer. Target mix at launch is roughly 50% Basic, 35% Comfort, 15% Comfort+. Comfort is the anchor — most field pitches should default to recommending it.

| Feature | BASIC | COMFORT | COMFORT+ |
| --- | --- | --- | --- |
| Monthly fee | $14.95/mo | $22.95/mo | $34.95/mo |
| Annual fee (10% discount) | $159 / yr | $248 / yr | $378 / yr |
| Tune-ups per year | 2 (Spring + Fall) | 2 + 1 Heating IAQ check | 2 + Quarterly Filter Service |
| Diagnostic / trip fee | Standard | Waived | Waived |
| Repair labor discount | 10% | 15% | 20% |
| Equipment / install discount | 5% | 10% | 15% |
| Priority scheduling | — | Same-day if before 11 AM | Guaranteed same-day |
| After-hours diagnostic | Standard rate | Standard rate | 50% off |
| Transferable to new owner | — | Yes | Yes |
| Transferable to new home | — | — | Yes (within service area) |
| Free condenser coil rinse | Once / yr | Twice / yr | Quarterly |
| Free 1" filter replacement | — | 2 / yr | Unlimited (custom sizes too) |
| Refrigerant top-off (R-410A) | — | 1 lb included | Up to 3 lbs included |
| IAQ inspection report | Annual | Annual + recommendations | Annual + free UV bulb check |
| Service Plan Member badge | Email signature | Yard sign offered | Yard sign + window decal |
| Loyalty referral bonus | $50 credit | $100 credit | $150 credit |

## Pricing rationale

- Basic at $14.95/mo undercuts the typical "$20 tune-up plan" found at competitors and acts as the loss-leader to recruit members.

- Comfort at $22.95/mo sits at the sweet spot of perceived value vs price; the math works because of higher ancillary revenue (members buy more).

- Comfort+ at $34.95/mo (under $1.20/day) targets the 15% of customers who own multi-zone, premium, or older systems where the included refrigerant + filters more than pay for the membership.

- All tiers offer a 10% discount when paid annually (12 months at the price of ~11) to lift cash-up-front conversion.

# 2. Financial Model — Year 1

Assumes 10% take-rate against the 39,951-customer base (= 4,000 members), distributed 50/35/15 across Basic/Comfort/Comfort+. Ancillary revenue is the additional non-membership revenue members generate (parts, upgrades, accessory installs, etc.) — based on industry data showing members spend 2-3x more than non-members on incremental services.

| Metric (Year 1) | Basic | Comfort | Comfort+ | Total |
| --- | --- | --- | --- | --- |
| Target adoption mix | 50% | 35% | 15% | 100% |
| Members @ 10% take-rate | 2,000 | 1,400 | 600 | 4,000 |
| Monthly fee | $14.95 | $22.95 | $34.95 | — |
| Annual recurring fee | $359K | $386K | $252K | $997K |
| Avg ancillary $ / member / yr | $110 | $210 | $340 | — |
| Ancillary revenue | $220K | $294K | $204K | $718K |
| TOTAL revenue | $579K | $680K | $456K | $1.71M |
| Service-call cost / member | $72 | $94 | $160 | — |
| Service-call cost (total) | $144K | $132K | $96K | $372K |
| Contribution margin | $435K | $548K | $360K | $1.34M |
| Margin % | 75% | 81% | 79% | 78% |

## Sensitivity

- At 5% adoption (2,000 members): ~$855K Year-1 revenue, $670K margin

- At 10% adoption (4,000 members): ~$1.71M revenue, $1.34M margin

- At 15% adoption (6,000 members): ~$2.57M revenue, $2.0M margin

- At 20% adoption (8,000 members): ~$3.42M revenue, $2.67M margin

## Capital required

- Software setup (HCP Service Plans module): included in current subscription

- Marketing materials (printed brochures, yard signs, decals): ~$8K one-time

- CSR + tech training: 2 sessions × 4 hours = 8 hours per employee · ~$5K labor

- Sales spiffs to seed adoption (first 60 days): $50 per Basic / $75 Comfort / $100 Comfort+ sold = budget $20K

- Total launch capital: ~$33K. Payback at 10% adoption: under 2 weeks.

# 3. Operational Rollout — 90 Days

## Days 0-30: Setup

- Configure the three plans inside Housecall Pro Service Plans module (templates, billing cadence, included visits)

- Create the three recurring-job templates (Spring Tune-Up, Fall Tune-Up, IAQ Check) and attach them to each plan

- Set up the Stripe ACH + card processing (HCP integrates natively) for monthly auto-billing

- Design and order printed materials: tri-fold brochure, refrigerator magnet (member-only number), yard sign template, window decal

- Build the customer-facing comparison page on cowboysac.com (link from main nav)

- Tag every existing Previous Customer in HCP with a "Plan-Eligible" tag (use the API)

## Days 30-60: Soft Launch

- Train all 12 CSR/office staff and all 48 field techs in 2 sessions each (use the pitch in Section 4 below)

- Soft launch to the 5,378 Previous Customer accounts via email + outbound CSR calls (~30 calls/day per CSR for 2 weeks)

- Every service call gets the plan pitch from the tech at the end ("would you like to lock this in for the year?")

- Members start receiving auto-scheduled tune-ups within 30 days of enrollment

- Spiff payouts kick in for CSRs and techs

## Days 60-90: Full Launch

- Marketing push to the full 39,951-customer database (email + direct mail to those without email)

- Yard signs go to first 50 members at the Comfort+ tier (free) and any Comfort member who opts in

- Inbound CSR script updated: every new customer is offered the plan during booking

- Weekly internal review: # of plans sold per CSR, per tech, mix, churn (cancellations)

- First quarterly review on day 90: actual vs target by tier, adjust pricing/benefits if mix is skewed

# 4. The Pitch — Scripts

## CSR script (inbound call)

After capturing the customer's needs and before scheduling, the CSR adds:

"Before we lock that in, one quick thing — we just launched our Comfort Club. For about $23 a month it includes both your spring and fall tune-ups, waives your diagnostic fee on this call, and gives you 15% off any repair. Most customers save the membership cost on the first visit alone. Want me to add it?"

If yes: enroll, complete booking, mention member benefit on this call.

If no thank you: proceed normally, no pressure. Tech will mention again at the door.

## Tech pitch (in-home, end of service call)

After the work is complete and the customer is happy, the tech adds:

"One thing before I go — Cowboy's just rolled out a service membership. For about $23 a month, your next two tune-ups are already paid for, plus any repairs you need over the next year are 15% off. Most members save $200-300 in their first year. Want me to set it up right here on the tablet? Takes 30 seconds."

If yes: enroll on the spot via HCP mobile, swipe the card, done.

If "let me think about it": leave the brochure + a refrigerator magnet with the office line and member-only number.

## Estimator pitch (during install proposal)

Comfort+ is included free for the first year on any system replacement. After year 1, customer can downgrade or cancel — but ~80% stay because they got used to the benefits.

# 5. Customer-Facing One-Pager (Brochure Copy)

## Headline

"Keep your AC running. Keep your wallet happy. Join the Cowboy's Comfort Club."

## Subheadline

Two tune-ups a year, priority scheduling when you need us, and discounts on every repair. From $14.95/month.

## Three benefit pillars

- AVOID THE BREAKDOWN. Two professional tune-ups per year catch small problems before they become $3,000 emergencies. Our members report 30% fewer mid-summer breakdowns.

- SKIP THE LINE. When it's 102° and your neighbor's AC just died, you get priority on the schedule. Members are booked first.

- PAY LESS. 10-20% off every repair. Waived diagnostic fees. Refrigerant included. Most members save more than their membership cost in the first year.

## Trust signals

- Family-owned and operated in San Antonio since [year]

- Trane Comfort Specialist dealer

- [X,XXX] 5-star Google reviews

- 100% money-back guarantee on your first 30 days — cancel anytime, no questions, full refund

## Call to action

"Call (210) 495-7771 or visit cowboysac.com/comfort-club. Mention your tech's name when you enroll today — they get a $50 thank-you."

# 6. Risks & Mitigation

## "What if too many people sign up and we can't service them?"

At 10% adoption, that's 8,000 tune-up visits per year (4,000 members × 2 visits). Spread across spring (Apr-Jun) and fall (Sept-Nov), that's roughly 1,300 visits/month during tune-up season. With 48 field techs averaging 4-5 jobs/day, capacity is there — and tune-ups protect the slow heating season. A staged rollout (start with the 5,378 Previous Customers) lets capacity scale naturally.

## "What if members start cancelling?"

Industry benchmark for HVAC member retention is 75-85% annual. Two design choices reduce churn: (1) the annual-pay discount (10% off) ties customers in for the year, (2) the loyalty referral bonus ($50-$150 credit) keeps members talking about the program.

## "Will it hurt our one-time service revenue?"

Members spend 2-3x more on incremental services than non-members (industry data). The membership doesn't replace one-time revenue — it locks the customer in and increases their lifetime spend. The risk is that ancillary revenue projections are conservative; the upside scenario is significantly larger.

## "What about commercial customers?"

This kit is residential-focused. A parallel Commercial Service Agreement program (covered as Strategic Gap G3 in the audit) is a separate workstream — different pricing, contract length, and SLA structure. Roll out residential first to prove the model, then build the commercial version once the residential program is steady.

# 7. Track Weekly · Decide Quarterly

Single dashboard, six metrics. Review weekly with the team. Make adjustments quarterly.

- Active members (count, by tier)

- New enrollments this week (by tier + by CSR/tech)

- Monthly recurring revenue (MRR) and annual recurring revenue (ARR)

- Churn rate (% of members who cancelled in the last 30 days)

- Member ancillary revenue (jobs sold to members beyond the included tune-ups)

- Avg revenue per member (ARPM) — total revenue from members ÷ active members

If churn exceeds 25% annualized in the first 90 days, the value/price ratio is off — adjust benefits before adjusting price. If new enrollments stall below 100/month after the soft launch, the pitch isn't landing — re-train CSRs and techs.